## Overview
Fuel Crisis Planning Guidance – Support at Home
Context
This workbook translates the draft fuel crisis guidance into a practical Excel tool for Support at Home providers. It focuses on short-term actions that are operationally practical, financially defensible, and aligned with current pricing and client agreement expectations.
Recommended Interim Position
Providers are encouraged to prioritise operational efficiencies—such as geographic rostering, visit consolidation, and reduction of travel intensity—as the primary response to rising fuel costs. Where necessary, providers may undertake targeted reviews of service pricing to ensure it reflects theperson centred care and cost of delivery; however, any adjustments must be proportionate, transparent, and aligned with published pricing and client agreement requirements. These measures may assist in the short term, but providers should continue to document impacts and escalate systemic cost pressures to Ageing Australia so advocacy can continue.
How to Use This Workbook
Sheet | Purpose
Overview | Summary of the position, principles, and workbook structure.
10-Step Plan | Short-term provider response plan with actions, outcomes, owners, and status tracking.
Action Checklist | Interim operational and pricing checklist with space to assign responsibility and note evidence.
Client Comms | Client communication planning tool and suggested messaging for affected clients.
Decision Principles
Safety first – do not compromise care quality or continuity.
Be fair and transparent – especially with clients and staff.
Try operational fixes before considering pricing changes as a last resort.
Keep changes proportionate, evidence-based, and documented.
Escalate systemic pressures early rather than carrying the burden alone.
One-line Summary
Act early, reduce travel wherever possible, work with clients on sustainable options, and escalate risks before services start to fail.
Workbook legend
Blue text | User input / owner or status fields intended to be edited. Track progress or fields needing attention.
Orange fill | Review notes or commentary areas.
Green fill | Approved wording / positive guidance anchors.
More Resources
National Fuel Security Plan | https://www.pmc.gov.au/resources/national-fuel-security-plan

## 10-Step Plan
Fuel Cost Crisis Plan – Support at Home Guide (Short-Term Response)
Purpose: Help providers maintain safe, continuous care while managing rapid increases in fuel costs and travel-related pressures.
Step | Focus | What to do | Outcome / key point | Suggested owner | Timeframe | Status | Notes / evidence
1 | Get a clear picture (within 1–2 weeks) | Identify which clients/areas require the most travel; identify services costing more to deliver than they bring in; map high-travel runs and gaps between visits. | You know where the problem actually is; not all services will be affected equally. | Operations / Scheduling | 1–2 weeks | Not started
2 | Act quickly on rostering | Group clients by location (suburb/postcode); assign staff to one area per shift where possible; reduce back-and-forth travel across large distances. | Immediate reduction in fuel use without changing pricing. | Scheduling | Immediate | Not started
3 | Adjust how services are delivered | Where safe, combine services into fewer visits; increase visit length instead of frequency; review short visits requiring disproportionate travel. Must still meet client needs and care plan requirements. | Improves efficiency without reducing intended care outcomes. | Care management / Operations | Immediate | Not started
4 | Identify high-risk services/clients | Flag long-distance clients, regional or remote services, and clients requiring multiple short visits. Ask whether delivery remains safe and sustainable. | High-risk areas are surfaced early for action. | Operations / Clinical leads | Weekly review | Not started
5 | Have early conversations with clients | Explain that travel costs have increased and you are trying to maintain services. Offer options such as updated pricing (if needed) or adjusted service schedules. Focus on continuity, not cost recovery. | Reduces complaint risk and improves client acceptance. | Care managers | Early / proactive | Not started
6 | Review pricing (last resort) | Contact Ageing Australia for guidance on any 'last resort' unavoidable price changes. Do not apply blanket increases or informal surcharges. Always ensure published pricing is up to date. Any changes require adequate notice and client consent. | Pricing changes are last resort only, are proportionate, transparent, and defensible. | Finance / Leadership | As required | Not started
7 | Support your workforce | Check whether workers are absorbing fuel costs. Consider temporary travel support and better alignment of shifts to reduce travel. | Supports workforce retention and service continuity. | People & culture / Operations | Immediate | Not started
8 | Monitor risk weekly | Track missed or delayed visits, staff availability, client complaints, and services operating at financial loss. Escalate internally if continuity is at risk or areas become unserviceable. | Live risk visibility rather than nasty surprises. | Leadership / Risk | Weekly | Not started
9 | Escalate early | Document cost increases and service impacts. Raise issues through peak bodies and government channels, including Ageing Australia. | Strengthens the case for sector-wide support. | Executive / Policy | Ongoing | Not started
10 | Last resort – viability decisions | If nothing else works, consider changing delivery methods or whether you can continue servicing certain clients or areas. Follow proper process, assess client risk, and document decisions. | Viability decisions are controlled, evidence-based, and defensible. | Executive / Risk | Only if required | Not started
Key Principles:
• | Safety first – do not compromise care.
• | Be fair and transparent with clients and staff.
• | Operational fixes should come before pricing changes.
• | Document everything, especially difficult decisions.

## Action Checklist
Provider Interim Action Checklist – Managing Fuel Cost Pressures
Purpose: Support providers to manage rising fuel costs in a way that is operationally practical, financially responsible, and aligned with current Support at Home Legislation, Aged Care Quality Standards and Support at Home pricing requirements.
1. Review service delivery efficiency
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Cluster client visits geographically (postcode/suburb zoning) | Priority action to reduce fuel usage per delivered hour |  |  | Not started
Implement run-based rostering (one worker, one area, one shift) | Priority action to reduce fuel usage per delivered hour |  |  | Not started
Reduce fragmented scheduling and travel gaps between visits | Priority action to reduce fuel usage per delivered hour |  |  | Not started
Prioritise consistent worker-client allocation | Reduces avoidable travel and improves continuity |  |  | Not started
2. Optimise visit structure
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Review short-duration visits for efficiency | Must align with assessed needs and documented care plan |  |  | Not started
Combine services into fewer, longer visits where appropriate | Must align with assessed needs and documented care plan |  |  | Not started
Adjust frequency versus duration in consultation with the client | Client discussion required; document agreement |  |  | Not started
3. Reassess cost of service delivery
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Recalculate cost per hour including updated travel inputs | Pricing review, not blanket increases |  |  | Not started
Identify services or locations operating at a loss | Use evidence to support any targeted review |  |  | Not started
Consider targeted price adjustments where justified but only as a last resort | Prices must remain published, up to date and proportionate |  |  | Not started
4. Geographic pricing differentiation
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Review metro vs outer metro vs regional cost differences | Supports more defensible cost-reflective pricing |  |  | Not started
Apply location-based pricing where travel intensity is higher but only as a last resort | Preferable to across-the-board increases |  |  | Not started
5. Review service area boundaries
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Define or refine service catchment zones | Prospective approach for new work and planning |  |  | Not started
Assess viability of servicing high-travel locations | Avoid abrupt changes for existing clients without risk assessment |  |  | Not started
6. Strengthen workforce travel settings
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Review km reimbursement and travel allowance settings | Maintains workforce participation and continuity |  |  | Not started
Introduce targeted incentives for high-travel shifts | Target support where pressure is greatest |  |  | Not started
Consider compressed or geographically aligned shifts | Reduces unnecessary travel burden |  |  | Not started
7. Optimise internal cost controls
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Reduce non-productive travel time between visits | Operational control action |  |  | Not started
Review fleet versus private vehicle usage | Assess most efficient model |  |  | Not started
Improve scheduling systems and routing | Use better planning rather than heroic improvisation |  |  | Not started
8. Engage clients transparently
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Explain changes to service structure where required | Maintain consistency with older person rights and care planning obligations |  |  | Not started
Discuss combining services to support continuity | Focus on sustainable care delivery |  |  | Not started
Reinforce the shared goal of sustainable care delivery | Keep tone constructive and client-centred |  |  | Not started
9. Consider alternative delivery modes
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Use telehealth for care management or reviews where suitable | Only where clinically and operationally appropriate |  |  | Not started
Supplement in-person visits with phone-based supports | Can reduce travel intensity in limited scenarios |  |  | Not started
10. Governance and risk oversight
Checklist item | Requirement / rationale | Owner | Due date | Status | Evidence / comment | Priority
Identify services or locations at financial risk | Escalate early rather than waiting for failure |  |  | Not started
Contact Ageing Australia first and document issues prompting changes to pricing | Essential for defensibility and governance |  |  | Not started
Escalate systemic issues to Ageing Australia | Supports sector advocacy |  |  | Not started

## Client Comms
Client Communication Plan – Fuel Cost Impacts
Purpose: Ensure clients are informed early, treated fairly, and involved in decisions where service delivery or pricing may be affected.
Step | Communication guidance | Why it matters | Who to contact / consider | Status | Notes | Do | Avoid
1 | Identify who needs to be contacted | Focus on clients in high-travel areas, receiving multiple short visits, or likely to be affected by service changes or pricing reviews. | Avoid unnecessary concern for unaffected clients. | Not started |  | Target likely impacted clients | Do not message everyone
2 | Start early and be proactive | Do not wait until services are at risk or a price change is implemented. Flag that travel-related costs are increasing and reassure clients you are working to maintain services. | Early notice reduces surprise and distrust. | Not started |  | Start before crisis point | Do not wait for a blow-up
3 | Use plain, honest language | Say: “The cost of getting to clients has increased significantly” and “We’re reviewing how we deliver services to keep them sustainable”. | Plain language is clearer and more defensible. | Not started |  | Keep wording simple | Avoid jargon and internal funding language
4 | Focus on continuity of care, not cost recovery | Frame the message as wanting to keep supporting the client safely and reliably. | More effective and more defensible. | Not started |  | Emphasise continuity | Avoid sounding like pure price recovery
5 | Offer options | Where changes are needed, offer choices: adjusted service frequency/duration, scheduling changes to reduce travel, or updated pricing (as last resort). | Clients are more likely to accept changes if they feel involved. | Not started |  | Present choices | Do not present a single forced outcome
6 | Have the conversation, not just a letter | Best approach is care manager discussion by phone or in person, followed by written confirmation. | Human contact reduces confusion and complaint risk. | Not started |  | Talk first, then confirm in writing | Avoid letter-only changes
7 | Allow time for decision-making | Give reasonable notice and time for questions, family input, or representative involvement. | Supports fairness and informed consent. | Not started |  | Allow time to consider | Avoid rushed decisions
8 | Document everything | Record what was explained, what options were provided, and the client response. | Critical if complaints or disputes arise. | Not started |  | Keep records | Do not rely on memory
9 | Tailor approach for vulnerable clients | For clients with cognitive impairment, high clinical needs, or limited supports, involve representatives and ensure changes do not create risk. | Protects vulnerable clients and reduces harm. | Not started |  | Tailor the approach | Avoid one-size-fits-all communication
10 | Plan for pushback | Some clients will decline changes; remain calm and consistent, reiterate options, and document outcomes. | Keeps the process controlled and respectful. | Not started |  | Prepare scripts and escalation paths | Avoid defensive responses
Suggested Client Message
“We want to let you know that the cost of delivering services—particularly travel—has increased due to price increases and fuel scarcity. We are reviewing how we deliver services to make sure we can continue supporting you safely and reliably. Your care manager will contact you to talk through some options and make sure your services continue in a way that works for you.”
Key principle: Be early, be clear, and give clients choices.